## Quick Release Letter
Request for Quick Release Letter Table
Applicant
Emergency Repair | Location | Funds Requested | Justification
Example: Culvert Replacement | Mile Post 10, Rt 101 | 150000 | Access to private residences Culvert washed out
Example: Bridge Replacement | Mile Post 20, Rt 101 | 150000 | Vital link serving local hospital.

## Quick Release Letter Response
Request for Quick Release Letter Table
Applicant |  |  |  | Division Engineer
Emergency Repair | Location | Funds Requested | Justification | Approved/ | Reason
Disapproved
Example: Bridge Replacement | Mile Post 10, Rt 101 | 150000 | Access to private residencesCulvert washed out | Disapproved | Alternate access available.
Example: Bridge Replacement | Mile Post 20, Rt 101 | 150000 | Vital Link serving local hospital. | Approved

## DSR Form
FEDERAL HIGHWAY ADMINISTRATION, Federal Lands Highway |  |  |  |  | Sheet No: |  | of
DAMAGE SURVEY REPORT |  |  |  |  | DSR No:
(Title 23, Federal-Aid System/Federal Domain) |  |  |  |  | Disaster No:
Applicant: |  |  | County: | State: | Inspection Date:
Location of Damage (Route No., Name of Road and Mile Post) |  |  |  |  | ADT:
Bridge Data: |  | Road Data: | Classification: |  | Photograph #:
Type: |  | Traveled Way Width: | Surface Type: | Thickness:
ID#: |  | Shoulder Width: | Surface Type:
Description and Cause of Damage: |  |  | Scope/Description of Repair:
COST ESTIMATE for EMERGENCY REPAIRS*
Quantity | Unit | Item Description |  |  |  | Unit Price | Cost
0
0
0
0
0
0
0
Proposed: Force Account Contract Total Emergency Repairs | [6 empty] | 0
COST ESTIMATE for PERMANENT REPAIRS*
Quantity | Unit | Item Description |  |  |  | Unit Price | Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Subtotal Permanent Repairs (continuation sheet) |  |  |  |  | 0
Proposed: Force Account Contract |  |  |  | Total Permanent Repairs |  |  | 0
Identify Betterment, if any, and provide justification* |  |  |  | Preliminary Engineering |  |  | 0
|  |  |  | Construction Engineering |  |  | 0
|  |  |  | Right-of-Way |  |  | 0
Other
|  |  |  | TOTAL ESTIMATED COST (Emergency and Permanent Repairs) |  |  | 0
Submitted By: (Name and Title) |  |  |  | Signature: |  |  | Date:
Reviewed By: (Name and Title) |  |  | Eligible Ineligible | Signature: |  |  | Date:
Recommended By: (Name and Title) |  |  | Eligible Ineligible | Signature: |  |  | Date:
*Attach Supplemental Sheets if necessary

## Continuation Sheet
FEDERAL HIGHWAY ADMINISTRATION, Federal Lands Highway |  |  | Sheet No: | of
DAMAGE SURVEY REPORT (Supplemental Sheet) |  |  | DSR No:
(Title 23, Federal-Aid System/Federal Domain) |  |  | Disaster No:
Applicant: | County: | State: | Inspection Date:
Location of Damage (Route No., Name of Road and Mile Post) |  |  | ADT:

## Estimate Continuation sheet
FEDERAL HIGHWAY ADMINISTRATION, Federal Lands Highway |  |  |  |  | Sheet No: |  | of
DAMAGE SURVEY REPORT (Supplemental Sheet) |  |  |  |  | DSR No:
(Title 23, Federal-Aid System/Federal Domain) |  |  |  |  | Disaster No:
Applicant: |  |  | County: | State: | Inspection Date:
Location of Damage (Route No., Name of Road and Mile Post) |  |  |  |  | ADT:
COST ESTIMATE
Quantity | Unit | Item Description |  |  |  | Unit Price | Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Continuation Sheet Subtotal | [6 empty] | 0

## POP Table
Program of Projects Table
Program of Projects Number: Date:
Disaster Number: Agency Sub_Unit:
DAMAGE SURVEY REPORT NUMBER | DESCRIPTION OF REPAIR | PREVIOUSLY APPROVED PROGRAM DOLLAR AMOUNT OF POP NUMBER_________________ |  |  |  | PERMANENT REPAIR METHOD
Site Number | Bold/Italic row(s) affected by change | Applicant (NPS) | Federal Lands Highway Division Office | Other includes Tribe, State, Agency, County | Total | Force Account/Contract/Other
0
0
0
0
0
0
0
0
0
| Program Totals | 0 | 0 | 0 | 0
Revised Date:
Revision/Change(s)
DAMAGE SURVEY REPORT NUMBER | DESCRIPTION OF REPAIR | CURRENT APPROVED CHANGES IN PROGRAM AMOUNT |  |  |  | PERMANENT REPAIR METHOD
Site Number | Bold/Italic row(s) affected by change | Applicant | Federal Lands Highway Division Office | Other includes Tribe, State, Agency, County | Total | Force Account/Contract/Other
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
0 | 0 |  |  |  | 0 | 0
REVISIONS TOTAL |  | 0 | 0 | 0 | 0
Revised Date:
Revised Program of Projects
DAMAGE SURVEY REPORT NUMBER | DESCRIPTION OF REPAIR | APPROVED PROGRAM AMOUNT FOR POP NUMBER_____________ |  |  |  | PERMANENT REPAIR METHOD
Site Number | Bold/Italic row(s) affected by change | Applicant | Federal Lands Highway Division Office | Other includes Tribe, State, Agency, County | Total | Force Account/Contract/Other
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
REVISED APPROVED PROGRAM TOTAL |  | 0 | 0 | 0 | 0

## POP Summary
Program of Projects Summary Table
Location of Damage | Organization Performing the Repairs | Previously Approved Amount | Current Approved Amount | Total Approved Amount
Mt Rainier | NPS | 0 | 468949 | 468949
| WFLHD | 0 | 176000 | 176000
N. Cascades
Subtotal | NPS | 0 | 468949 | 468949
| WFLHD | 0 | 176000 | 176000
Grand Total |  | 0 | 644949 | 644949

## Request forTime Extension
Request for Time Extension Table
Damage Survey Report Number | Current Approved Contract Award Date | Revised Contract Award Date Requested | Rationale for Request for Revision of the Contract Award Date
Example: BLU 2300-4.9 | Example: Date | Example: Date | Example: We cannot access this site because of road damage along Route 6 that occurred in the OR98-2-BIA disaster. The damage at M.P. 1.0 has severely damaged the bridge abutment and it will not be repaired until later this fall.

## Time Extension Table
Time Extensions Table
Damage Survey Report Number | Revised Contract Award Date Requested | Approved Contract Award Date | Rationale for Decision Made
Example: BLU 2300-4.9 | Example: Date | Example: Date | Example: The time extension is approved based on another eligible ERFO disaster delaying the repair of this site. We expect that the repair of this site will be accomplished along with the repair of the bridge abutment at MP 1.0.

## ERFO Funds Request
ERFO FUNDS REQUEST FOR FY _____
Agency Administering ERFO Repairs | Disaster Number | Reimbursement (Payback) Funds |  | (3) | (4)
|  |  |  | Amount of Funds needed for Ongoing Projects | Amount of Funds needed for this Fiscal Year | Totals
|  | (1) Agency Funds | (2)
Federal Lands Highway
|  | $ | $ | $ | $ | $
|  | $ | $ | $ | $ | $
|  | $ | $ | $ | $ | $
|  | $ | $ | $ | $ | $
|  | $ | $ | $ | $ | $
Total |  | $ | $ | $ | $ | $
Prepared by: _____________________________________ Date:_________________ Phone:_____________
(1) Amount of Agency funds used on repairs to be repaid by ERFO.
(2) Amount of Federal Lands Highway Program funds used on repairs to be repaid by ERFO
(3) Amount of ERFO funds needed for Construction Engineering(CE)/Contract Modifications (CM) for active/ongoing construction projects.
(4) The amount of funds needed for design, advertisement, award, and construction engineering for new projects this fiscal year.

## Repair Status-Close Out
DISASTER REPAIR STATUS/CLOSEOUT REPORT
Date: ____________________________ Disaster Number: ________________________ Sub-Unit: _________________________
LOCATION DAMAGE SURVEY REPORT NUMBER | NTTFI or NFLTFI (Y/N) | DESCRIPTION OF APPROVED REPAIR | APPROVED PROGRAM OF PROJECTS |  |  |  | CURRENT OBLIGATIONS/ FINAL EXPENDITURES |  |  |  |  | ERFO CLOSEOUT AMOUNT | (Anticipated/ Actual) Contract Award Date | (Anticipated/ Actual) Construction Completion Date | Date Closed
|  |  | Applicant | FLH Division Office | FLH TTP Office | TOTAL | Applicant | FLH Division Office | FLH TTP Office | Non-ERFO funds used | TOTAL
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The submitted expenditures are the actual costs incurred to complete only approved eligible repairs. Attach a separate sheet to explain any deviations. Signed: _______________________________ Date: ________________________