## Section 104. — CONTROL OF WORK

06/15/2022– FP-14

WFL Specification 09/17/18 1040010

Include the following in all projects.

### 104.03 Specifications and Drawings.

Amend as follows:

Delete the first paragraph of Subsection (a) and substitute the following:

**(a) General.** Submittals include both documents and drawings required to construct the work. Review submittals for accuracy, completeness, and compliance with the contract. Verify submittals according to Section 153. Submittals that do not include evidence of Contractor verification may be returned for resubmission.

Submit documents in an electronic format for approval. Submit drawings in both paper and electronic format for approval. See Subsection 103.06.

Time for approval starts over when submittals are returned for revision or if additional information is requested by the CO. Do not perform work related to submitted documents or drawings before approval of the CO. Obtain written approval before changing or deviating from the approved submittals.

Delete Subsection (a)(1) and substitute the following:

**(1) Documents other than drawings.** Documents other than drawings include descriptive literature, illustrations, schedules, performance and test data, certifications, and similar material submitted by the Contractor to certify or explain, in detail, specific portions of the work required by the Contract. Allow 14 days for approval by the CO unless otherwise specified.

Delete the first sentence in the last paragraph of Subsection (a)(2) and substitute the following:

Submit 3 paper sets of drawings, and an electronic set of drawings with supporting calculations.

WFL Specification 11/12/20 1040020

Include the following in projects containing concrete box culverts when no load ratings are required.

Coordinate with WFL Structures to determine the need for load ratings.

Delete Subsection (b)(2)*(i)* and substitute the following:

*(i)* Concrete box culvert, headwall, and wingwall details;

WFL Specification 11/12/20 1040025

Include the following in projects containing concrete box culverts when load ratings are required.

Coordinate with WFL Structures to determine the need for load ratings.

Delete Subsection (b)(2)*(i)* and substitute the following:

*(i)* Concrete box culvert with load ratings and supporting calculations, headwall, and wingwall details, precast or cast-in-place concrete foundations

**WFL Specification 08/01/19 1040030**

**Include the following in projects containing temporary bridge structures.**

Delete Subsection (b)(3)*(d)* and substitute the following:

*(d)* Temporary bridge structures for public use, and load ratings for temporary bridge structures for public use.

WFL Specification 09/17/18 1040040

Include the following in MATOC projects.

### 104.04 Coordination of Contract Documents.

Delete the text of this Subsection and substitute the following:

The FAR, TAR, Basic Contract, special contract requirements, plans, and standard specifications are contract documents. A requirement in one document is binding as though occurring in all the contract documents. The contract documents are intended to be complementary and to describe and provide for a complete contract. In case of discrepancy, calculated and shown dimensions govern over scaled dimensions. The contract documents govern in the following order:

**(a)** Federal Acquisition Regulations;

**(b)** Transportation Acquisition Regulations;

**(c)** Basic IDIQ Contract;

**(d)** Special Contract Requirements (SCRs);

**(e)** Plans; and

**(f)** Standard specifications.

WFL Specification 06/15/2022 1040042

Include the following in all projects.

### 104.05 Load Restrictions.

 Amend as follows:

Add the following:

Unless otherwise permitted, do not operate equipment or vehicles that exceed the legal load limits over new or existing structures. Submit a plan to utilize existing or new structures as temporary works or work platforms according to Section 562.

WFL Specification 11/12/20 1040045

Include the following with:

1. NPS projects, and;

2. When the *FLH Bridge Oversized/Overweight Permit Load Request* form is provided as physical data

Add the following:

Submit oversized and overweight permit requests for non-legal loads transported within the [INSERT PARK NAME] National Park boundary. Use the *FLH Bridge Oversized/Overweight Permit Load Reques*t form listed under FAR Clause 52.236-4 Physical Data (Apr 1984).

WFL Specification 01/01/14 1040050

Include the following when other contracts in close proximity may have an effect on this project. List point of contact if applicable.

### 104.06 Other Contracts.

(Added Subsection).

Follow the requirements of FAR Clause 52.236-8 Other Contracts.

[INSERT LANGUAGE].